🛡️

PhishGuard

Phishing Email Identification Tool

Project Scope Document

Version 1.0  |  March 2026

Target Completion: April 13, 2026

# 1. Executive Summary

PhishGuard is a zero-budget, open-source phishing email identification tool powered by a traditionally trained machine learning model. The tool will allow users to paste or upload email content and receive an instant prediction on whether the email is a phishing attempt, along with a confidence score and a human-readable explanation of the key signals detected.

The project will be completed within 30 days using exclusively free, open-source software, publicly available datasets, and free-tier hosting platforms. The primary delivery will be a functional web application accessible to general consumers, IT professionals, and educators.

| Attribute | Detail |
| --- | --- |
| Project Name | PhishGuard – Phishing Email Identification Tool |
| Budget | $0 (open-source / free-tier only) |
| Timeline | 30 days (March 13 – April 13, 2026) |
| Primary Interface | Web application (paste email text / upload .eml) |
| Target Users | General consumers, IT security professionals, educators |
| ML Approach | Traditional ML (scikit-learn) + NLP feature engineering |
| Hosting | Hugging Face Spaces or Render (free tier) |

# 2. Project Objectives

## 2.1 Primary Goals

- Train a machine learning classifier capable of distinguishing phishing emails from legitimate ones with high accuracy (target: >95% accuracy on held-out test set).

- Build a clean, intuitive web UI where users can paste email text or upload an .eml file and receive an instant analysis.

- Provide interpretable output — not just a binary label, but a confidence score and the specific red flags detected (e.g., suspicious links, urgency language, spoofed sender).

- Deploy the finished application on a free hosting platform accessible via public URL.

## 2.2 Secondary Goals

- Maintain a fully open-source, reproducible codebase on GitHub.

- Document the training pipeline so the model can be retrained with fresh data in the future.

- Include a short educational component explaining why a flagged email is suspicious, turning the tool into a learning resource.

## 2.3 Out of Scope

- Real-time email client integration (Gmail plugin, Outlook add-in) — post-v1 roadmap only.

- User accounts, login systems, or persistent history storage.

- Attachment scanning (PDF, DOCX malware detection) — text-only analysis in v1.

- Paid APIs, paid cloud compute, or any recurring financial cost.

# 3. Scope of Work

## 3.1 Data Collection & Preparation

The model will be trained on publicly available, labeled email datasets. No data collection infrastructure needs to be built — existing curated datasets will be used directly.

Primary Datasets (all free)

- SpamAssassin Public Corpus: CLAIR Phishing Email Dataset

- Nazario Phishing Corpus: ~5,000 real phishing emails from 2019–2023

- UCI Spam/Ham Collection: Enron Email Dataset (legitimate email baseline)

Data preparation tasks will include:

- Email parsing: extract subject, body, sender, reply-to, and embedded URLs

- HTML stripping and text normalization

- Deduplication and class balancing (target ~50/50 phishing/legitimate split)

- Train / validation / test split (70% / 15% / 15%)

## 3.2 Feature Engineering

Rather than using raw text embeddings (which require large models and GPU compute), the model will be built on handcrafted NLP features — lightweight, interpretable, and CPU-friendly.

Feature Categories

- Urgency & pressure language — keyword frequency scoring ("act now", "account suspended", "verify immediately")

- URL analysis — number of URLs, mismatched display text vs. href, URL entropy, suspicious TLDs, use of URL shorteners

- Sender/header anomalies — reply-to ≠ from, display name spoofing, free email domain usage for corporate impersonation

- Structural signals — excessive HTML obfuscation, image-to-text ratio, missing/generic salutation

- TF-IDF features — top n-gram features extracted from subject and body

- Readability metrics — Flesch-Kincaid grade, punctuation density, all-caps ratio

## 3.3 Model Training

Multiple classical ML algorithms will be evaluated and compared. The best-performing model will be selected for production use.

| Algorithm | Rationale | Library |
| --- | --- | --- |
| Random Forest | Strong baseline; handles mixed features well; interpretable feature importances | scikit-learn |
| Gradient Boosting (XGBoost / LightGBM) | High accuracy on tabular data; fast inference | xgboost / lightgbm |
| Logistic Regression | Fast; interpretable coefficients; good calibrated probabilities | scikit-learn |
| Naive Bayes | Classic spam filter baseline; efficient on text features | scikit-learn |

Evaluation metrics: Accuracy, Precision, Recall, F1-Score, and AUC-ROC. False negatives (missed phishing) are treated as more costly than false positives — the threshold will be tuned accordingly.

## 3.4 Web Application

The frontend will be a clean, single-page application. The backend will serve the trained model via a REST API.

Core UI Features

- Text area for pasting raw email content

- File upload support for .eml and .txt formats

- "Analyze" button with a loading spinner for feedback during inference

- Result card displaying: Verdict (Phishing / Legitimate), Confidence score (0–100%), and a bulleted list of detected red flags with short explanations

- "Why is this suspicious?" expandable section for educational context

## 3.5 Deployment

- Model serialized with joblib and stored in the repository

- Backend API: FastAPI served via Uvicorn

- Hosted on Hugging Face Spaces (Gradio) or Render free tier

- GitHub Actions for automated testing on pull requests

# 4. Tech Stack

Every component below is free and open-source. No paid APIs, services, or compute is required.

| Layer | Technology | Version | Purpose |
| --- | --- | --- | --- |
| Language | Python | 3.11+ | All backend, ML, and scripting |
| ML Framework | scikit-learn | 1.4+ | Model training, evaluation, pipelines |
| Boosting | XGBoost / LightGBM | Latest | Gradient boosting classifiers |
| NLP | NLTK + spaCy | Latest | Tokenization, stopwords, entity detection |
| Email Parsing | Python email / mailparser | Stdlib | Parse .eml headers, body, URLs |
| Data Handling | pandas + NumPy | Latest | Feature engineering, data wrangling |
| URL Analysis | BeautifulSoup4 | Latest | HTML parsing, link extraction |
| Backend API | FastAPI + Uvicorn | Latest | REST API serving model predictions |
| Frontend | Gradio | Latest | Rapid web UI, natively hosted on HF Spaces |
| Serialization | joblib | Latest | Save/load trained model artifacts |
| Testing | pytest | Latest | Unit and integration tests |
| CI/CD | GitHub Actions | Free tier | Automated test runs on push |
| Hosting | Hugging Face Spaces | Free tier | Public deployment, zero infra cost |
| Version Control | Git + GitHub | Free | Source control, collaboration |
| Notebooks | Jupyter Notebook | Latest | Exploratory data analysis & experiments |

## 4.1 Why This Stack?

- Zero cost: Hugging Face Spaces, GitHub, and all libraries are completely free.

- CPU-only: Classical ML (Random Forest, XGBoost) runs efficiently without GPU — no cloud compute needed.

- Interpretability: Feature-based models expose which signals drove each decision, enabling the educational red-flag explanations.

- Gradio: The fastest path from trained model to shareable web UI — a full app can be deployed in ~20 lines of Python.

# 5. Project Timeline

Total duration: 30 days (March 13 – April 13, 2026). The project is broken into four phases with clear weekly milestones and daily actionable steps.

| Phase | Dates | Actionable Steps | Deliverable |
| --- | --- | --- | --- |
| Phase 1 Foundation & Data | Mar 13–19 (Week 1) | - Set up GitHub repo, virtual env, project structure - Download SpamAssassin, Nazario, Enron datasets - Write email parser (headers, body, URLs) - Run EDA — class distribution, length stats, common words - Build data cleaning & deduplication pipeline - Achieve clean, balanced train/val/test split | Cleaned dataset + EDA notebook |
| Phase 2 Feature Eng. & Model Training | Mar 20–28 (Week 2–3) | - Implement all feature extractors (URL, header, text, structural) - Build scikit-learn feature pipeline - Train baseline: Logistic Regression & Naive Bayes - Train and tune Random Forest (GridSearchCV) - Train and tune XGBoost / LightGBM - Compare models on val set; select winner - Tune classification threshold for low false-negative rate - Serialize final model with joblib | Trained model + evaluation report |
| Phase 3 Web App Build | Mar 29 – Apr 6 (Week 3–4) | - Build Gradio UI: text input, file upload, result card - Wire model inference to UI - Implement red flag explanation generator - Add confidence score display - Add educational 'Why is this suspicious?' panel - Write pytest unit tests for feature extractors - Set up GitHub Actions CI pipeline | Working local web app + test suite |
| Phase 4 Deployment & Polish | Apr 7–13 (Week 4) | - Deploy to Hugging Face Spaces - Verify public URL functionality end-to-end - Test with 20+ real-world email samples - Fix bugs identified in production testing - Write README with usage instructions - Document training pipeline for future retraining - Final review and project sign-off | Live public URL + docs |

# 6. Risks & Mitigations

| Risk | Likelihood | Mitigation | Owner |
| --- | --- | --- | --- |
| Dataset bias — training data doesn't reflect modern phishing tactics | Medium | Supplement Nazario corpus with recent phishing samples from PhishTank (free export) | Data Lead |
| Model overfitting to training set | Medium | Strict train/test split; cross-validation; early stopping in XGBoost | ML Lead |
| Hugging Face Spaces cold-start latency (free tier sleeps) | High | Implement loading screen UX; consider Render.com as fallback host | Dev Lead |
| Feature extractor fails on malformed HTML emails | Medium | Wrap all parsers in try/except; fall back to plain-text extraction | Dev Lead |
| Scope creep extending timeline beyond 30 days | Low | Strict out-of-scope list enforced; post-v1 backlog tracked separately | PM |

# 7. Success Metrics

The project will be considered successfully completed when all of the following criteria are met:

- >95% accuracy on the held-out test set with a false-negative rate (missed phishing) below 3%.

- Inference time of <2 seconds per email on a standard CPU.

- Web application publicly accessible via a stable URL with no authentication required.

- A minimum of 20 real-world emails manually tested and reviewed for correctness.

- GitHub repository is public with a complete README, setup instructions, and training documentation.

- All features listed in Section 3.4 are implemented and functional.

# 8. Post-v1 Roadmap (Out of Scope for This Project)

These features are explicitly excluded from the 30-day scope but documented here for future planning:

- Gmail / Outlook browser extension for real-time inbox analysis

- Attachment scanning (PDF, Office document macro detection)

- Fine-tuned BERT or DistilBERT model for improved language understanding

- Feedback loop — allow users to flag incorrect predictions to improve the model over time

- Multi-language support (phishing emails in non-English languages)

- API endpoint for developer integrations